## Description
COMP 5700/6700 -- Secure Software Process
Iteration: | 6
Objective: | To refine previously obtained process practices
Product: | Write software to solve the top layer
Deliverables: | Via Canvas: | Include this spreadsheet with completed process information with your Canvas submission.
| Via GitHub: | Push your code to GitHub Classroom
Notes on Process: | - Follow the process in the "Process" worksheet for this assignment.
- This homework assignment is be accomplished individually
- Ensure you follow the course coding and counting standards.
- Be honest in your data. Your grade depends on how you follow the process and the quality of your work, not on the speed of your work or the number of defects found.
- Below are clarifications for process worksheets that have been problematic in the past:
|  | Worksheet | Special Instructions
|  | In general | It isn't possible to predict ahead of time the exact number of yellow cells you will need. Most sheets contain extra rows to accommodate process data. Use only the cells that pertain to your development. Do not fill out every yellow cell just for the sake of filling out the spreadsheet. Use common sense.
|  | Plan | Record lines of code for production code only. Do not include test code.
|  | Acceptance | Develop acceptance tests for the specified black box. Do not include tests for items that are not part of the specifications (meaning, items over and above the specs -- these tests will appear in your individual unit test files). Write the expected results at planning time. Modify if necessary later. Don’t write actual results in advance. Actual results should reflect the state of the software at the time of delivery.
|  | Time Log | Use the "sandbox" activity to record time spent experimenting with the assignment requirements.
|  | Historical Data | Record your process and product data from all previous programming assignments. Do this as part of the planning activity.
|  | Review | During the planning activity, list a count of all defects that you've previously encountered. Construct a checklist from your defect logs. Indicate during the review activity the number of times the review checklist item found an error.
|  | Scenarios | Create an interface specification depicting the interaction between a test driver and the class specified above. Create nominal scenario(s) and anomalous scenario(s) sufficient to convey your understanding of software behavior
|  | Lessons Learned | This tab is optional. Use it to record great ideas, suggestions, etc. Whining is not productive :)
|  | Architecture | Develop CRC cards only for the production code needed to implement the specifications. Do not include CRC cards for test drivers.
|  | Estimate | Record all the items from your architecture. Do not include test code.
|  | Iterations | Record the number of iterations you plan to use, together with the planned velocity of each iteration. Record the amount of time you plan to have available each day of the project window. Please plan for more than one iteration.
Special Instructions: | - Selected cells in this spreadsheet are locked against inadvertent editing. Should you need to unlock the spreadsheet, select the protected worksheet, select Tools -> Protection -> unprotect.

## Process
Constants |  |  |  | 0
Start date: | 36526 |  | Grades: | 1
End date: | 73051 |  |  | 0.95
Phases: | Analyze | Identifying customer needs |  | 0.9
| Architect | High-level design |  | 0.85
| Plan project | Determine actions/effort for project duration |  | 0.8
| Plan iteration | Determine actions/effort this iteration |  | 0.75
| Construct | Low-level design, coding, unit testing |  | 0.7
| Refactor | Restructure internal design |  | 0.65
| Review | Examine test code for risk mitigation |  | 0.5
| Integration test | End-to-end test of components to date
| Repattern | Restructure external design
| Postmortem | Capture post-development statistics
| Sandbox | Prove ideas, try concepts
Defect Types: | Requirements Change | Changes to requirements | Iteration | did not follow
| Requirements Clarification | Clarifications to requirements |  | very painful
| Product syntax | Syntax flaws in the deliverable product |  | painful
| Product logic | Logic flaws in the deliverable product |  | neutral
| Product interface | Flaws in the interface of a component of the deliverable product |  | helpful
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | very helpful
| Test syntax | Syntax flaws in the test code
| Test logic | Logic flaws in the test code
| Test interface | Flaws in the interface of a component of the test code
| Test checking | Flaws with boundary/type checking within a component of the test code
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 0
Y/N: | Yes |  |  | 0
| No |  |  | 0
Proxy Types: | - |  |  | Base
| Calculation |  |  | New
| Data |  |  | Reusable
I/O
Logic
Sizes: | VS | S | M | VL
upper | -1.5 | -0.5 | 0.5 | 99999
mid | -2 | -1 | 0 | 2
lower | 0 | -1.5 | -0.5 | 1.5
| 0 | 0 | 0
<-- Mandatory |  | ✔
Process Script
Minimal Guiding Indicators |  |  |  | Minimal Sufficient Activities
| Goal | Indicator |  |  | Engineering Activities
| Cost: | None |  |  | Envision
| Schedule: | On time |  |  | Analyze
| Performance: |  |  |  | Synthesize
| Product: |  |  |  | Architecture
| NFR: | None |  |  | Articulate
| FR: | Equivalence Class Partitioning |  |  | Construct
| Process: | Completed spreadsheet |  |  | Interpret
Integration Test
Operational Activities
Plan
Plan project
Monitor/Control
Post Mortem
Release
Minimal Viable Process |  |  |  | Minimal Effective Practices
|  |  |  | MSA | MEP | Spreadsheet tab on which to document MEP
|  |  |  | Pre-project | • Switch to an iteration-specific local branch
|  |  |  | Analysis | • Write as many acceptance tests as you feel are necessary to understand the assignment | Acceptance
|  |  |  | Architect | • Create CRC cards for each component you plan to build/modify | Architecture - Pre
|  |  |  | Plan Project | • Estimate projected LOC | Estimation
[5 empty] | • Estimate projected effort | Estimation
[5 empty] | • Construct review check list | Review
|  |  |  | Construction | • Repeat
• • Select/write a test case
[5 empty] | • • Run the test as a red light test | Acceptance (if test is an acceptance test)
• • While the test is not red
• • • Diagnose why the test was not red
• • • If the problem was due to incorrect test code
• • • • Fix the defect
• • • • Run the test as a red light test
• • • Else
• • • • Continue to the next red light test
• • Build enough production code to make the test pass
• • Run the test as a green light test
• • While the test is not green
• • • Fix the defect
• • • Run the test as a green light test
• • Clean up the code as appropriate and run as blue light
• Until test coverage is sufficient and all tests pass
|  |  |  | Review | • Perform rubber duck review of test code | Review
|  |  |  | Refactor | • Refactor production code to remove odious smells; run as blue light
|  |  |  | Post Mortem | • Record acceptance test results | Acceptance
[5 empty] | • Count production LOC | Estimation
[5 empty] | • Record your CRC cards as of the time of submission | Architecture - Post
[5 empty] | • Record lessons learned (optional) | Lessons
|  |  |  | Release | • Commit all code to git
• Push branch to GitHub
• Merge iteration branch with master branch
• Push master branch to GitHub.com
• Upload spreadsheet to Canvas
|  |  |  | Monitor | • Record time spent in each activity. | Time Log
Minimal Guiding Indicators
Cost: |  | -
Schedule: |  | Submitted on time
Performance:
Product:
| NFR: | Meets delivery requirements.
| FR: | Boundary Value Analysis
| Process: | Evident on spreadsheet
Operational Engineering
Plan Project
Post Mortem
Release
Monitor
Construct
Not all components are constructed
Analyze
Review
Failed review
Refactor
Architect

## Spec Notes (hidden)
Specification Notes

## Customer Needs (hidden)
Customer Needs
Background: | We are building a software representation of Rubik's Cube (see https://en.wikipedia.org/wiki/Rubik%27s_Cube for background on the cube).
Our implementation will ultimately consist of microservices that provides a solution to a given Rubik's cube. Each individual microservice performs a specific cube function. When a microservice is passed information about the current state of the cube, it carries out its function and outputs a new cube state. The microservices serve as middleware, meaning, it operates without a user interface, and is triggered by an HTTP request. Information is carried to the microservice via a URL query string; the microservice returns information via an HTTP response. You will get some details in this assignment, with other details being explained incrementally in subsequent assignments.
This assignment asks you to write a microservice that solves a cube's down-face cross
Functional Specifications: | sudoku
|  | Abstraction: | dispatch performs a specific function based on information it receives.
| method |  | description
This functionality is provided for you ➜ |  | GET /rubik | Performs an operation on the Rubik's Cube model, where the operation and any accompanying parameters are specified by the query portion of the URL
|  |  | Invocation pattern: | https://name-of-server.com/rubik?op=solve&cube=bbbbbbbbggggggggyyyyyyyyrrrrrrrrwwwwwwwwoooooooo
|  |  |  | where | signifies
|  |  |  | name-of-server.com | name of the microservice provider
|  |  |  | rubik | name of the microservice
|  |  |  | op | operation to perform ("solve," in this particular case)
|  |  |  | cube | parameters used in performing the operation ("cube," in this particular case)
|  |  | Parameters: | Parameters to the microservice are specified in the query portion of the URL and must be in URL-legal format. All parameters arrive unvalidated. The "op" parameter is mandatory.
|  |  |  | Note: | Query string elements can occur in any order.
[5 empty] | Example: | ?parm1=123&parm2=XYZ
is equivalent to
?parm2=XYZ&parm1=123
|  |  |  | Note: | If names are duplicated in the query string, the leftmost value is associated with the name.
[5 empty] | Example: | ?op=op1&op=op2
results in
"op1" being used as the value of "op"
|  |  |  | Note: | Names in the query string may be designated as empty, in which case they have an empty string as a value. This should not be interpreted as a missing parameter.
[5 empty] | Example: | ?op=op1&parm1=&parm2=
results in
empty strings being used as the values of "parm1" and "parm2"
|  |  | Desired behavior (normal): | Performs the operation named by the 'op' parameter. Returns a string of a Python dictionary containing the results. Operations are:
|  |  |  | Operation Name | Operation Description
|  |  |  | op=check | Determines whether the cube has been solved or not
|  |  |  | op=create | Creates a solved cube
|  |  |  | op=info | Identifies the developer
A description of each operation is given in the "operation" section below.
|  |  | Desired behavior (errors): | If: | the query string contains no "op" parameter
|  |  |  | Action: | Return a dictionary element having a key of "status" and a value of "error: xxx", where xxx is a diagnostic string.
|  |  |  | Exit conditions: | No further processing takes place once an error is discovered.
|  |  | State change: | No state is retained by the microservice.
|  |  | General examples: | Valid values
|  |  |  | Input: | http://name-of-server.com/rubik?op=info
|  |  |  | Returns: | A string of a dictionary containing the results of the "info" operation
|  |  |  | Input: | http://name-of-server.com/rubik?op=check& cube=111111111222222222333333333444444444555555555666666666
|  |  |  | Returns: | A string of a dictionary containing the results of the "check" operation
Invalid values
|  |  |  | Input: | http://name-of-server.com/rubik
|  |  |  | Returns: | {'status':'error: no op is specified'}
|  |  |  | Input: | http://name-of-server.com/rubik? cube=aaaaaaaaabbbbbbbbbcccccccccdddddddddeeeeeeeeefffffffff
|  |  |  | Returns: | {'status':'error: no op is specified'}
|  |  |  | Input: | http://name-of-server.com/rubik?op=xyz
|  |  |  | Returns: | {'status':'error: op is not a legal operation'}
|  |  |  | Input: | http://name-of-server.com/rubik?op=
|  |  |  | Returns: | {'status':'error: no op is specified'}
|  |  | Implementation note: | Server interface code parses the HTTP request query string into a python dictionary and passes the dictionary to _dispatch() which, in turn, calls the component associated with the specified operation. Upon completion, a dictionary containing results is returned to _dispatch() and converted to a string the HTTP response. You should not have to modify microservice.py or dispatch.py. Modules for handling each of the operations have been stubbed and require your modification.
| operation |  | description
Iteration 1 Statement of Work➜ |  | op=create | Creates a solved cube
|  |  | Invocation pattern: | http://name-of-server.com/rubik?op=create&faces=123456
|  |  | Relevant dictionary elements: | key | content
|  |  |  | cube | This key-value pair models the physical Rubik's Cube. Its value is a 54-charaacter string where each character represents the 'color' of a corresponding element of the cube. The string consists of characters a-z, A-Z, 0-9 and contains no delimiters or extraneous white space. The string has 9 instances of 6 unique colors. The first 9 characters represent the colors of the elements on the front face, the second 9 characters represent the colors of the elements on the right face, and so forth for the back, left, top, and under faces, respectively. Each face's characters are arranged in row-major order, beginning with the upper left corner when looking at the face. The middle element of each face must be unique. Mandatory. Arrives unvalidated. The "Support Info" tab illustrates the layout of the cube.
Dictionary elements not specified above are ignored.
|  |  | Desired behavior (normal): | Returns a dictionary consisting of the following key-value pairs (see "Support Information" for examples):
|  |  |  | key | content
|  |  |  | status | This key-value pair indicates the status of the a valid cube. The value associated with status at creation time is "ok"
|  |  | Desired behavior (errors): | If: | any of the following pertain to cube:
*
|  |  | In priority order | Action: | Return a dictionary element having only a key of "status" and a value of "error: xxx", where xxx is an appropriate diagnostic string,
|  |  |  | Exit conditions: | And perform no further processing once an error is discovered.
Iteration 1 Statement of Work➜ |  | op=info | Identifies the developer
|  |  | Invocation pattern: | http://name-of-server.com/rubik?op=info
|  |  | Relevant dictionary elements: | The operation has no relevant dictionary elements
Extraneous dictionary elements are ignored.
|  |  | Desired behavior (normal): | Returns a dictionary consisting of the following key-value pairs:
|  |  |  | key | content
|  |  |  | user | The value associated with the key user is your 7-character AU user name.
|  |  | Desired behavior (errors): | Not applicable
Future Iteration ➜ |  | op=check | Determines whether the cube has been solved or not
|  |  | Desired behavior (normal): | Currently stubbed
Future Iteration ➜ |  | #REF! | #REF!
|  |  | Desired behavior (normal): | Currently stubbed
Future Iteration ➜ |  | #REF! | #REF!
|  |  | Desired behavior (normal): | Currently stubbed

## Assessment
Constants |  |  |  |  | 0
Start date: | 36526 |  | Grades: | AA | 1
End date: | 73051 |  |  | A | 0.95
Phases: | Analyze | Identifying customer needs |  | AB | 0.9
| Architect | High-level design |  | B | 0.85
| Plan project | Determine actions/effort for project duration |  | BC | 0.8
| Plan iteration | Determine actions/effort this iteration |  | C | 0.75
| Construct | Low-level design, coding, unit testing |  | CD | 0.7
| Refactor | Restructure internal design |  | D | 0.65
| Review | Examine test code for risk mitigation |  | F | 0.5
| Integration test | End-to-end test of components to date
| Repattern | Restructure external design
| Postmortem | Capture post-development statistics
| Sandbox | Prove ideas, try concepts
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful
| Test syntax | Syntax flaws in the test code |  | 6
| Test logic | Logic flaws in the test code |  | 7
| Test interface | Flaws in the interface of a component of the test code |  | 8
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0
Y/N: | Yes |  |  | Passed | 0
| No |  |  | Passed with issues | 0
Proxy Types: | - |  |  | Failed | Base
| Calculation |  |  | Not tested | New
| Data |  |  | Not applicable | Reusable
I/O
Logic
Sizes: | VS | S | M | L | VL
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999
mid | -2 | -1 | 0 | 1 | 2
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5
| 0 | 0 | 0 | 0
<-- Mandatory |  | ✔
Assessment Worksheet
Name: |  | Mary Mitchell
AU user name: |  | mem0250
GitHub Classroom URL: |  | https://github.com/SoftwareProcess/rubik-merrymitch.git
URL of microservice:
Instructor Assessment
Product Assessment
Process Assessment:
Score: |  | out of | 100
Grading rubric: Product Aspect
|  | 100 | Product passes all customer acceptance tests
|  | 90 | Product passes all customer happy path acceptance tests and fails no more than 10% of sad path tests
|  | 80 | Product fails no more than 10% of customer happy path acceptance tests and fails no more than 20% of sad path acceptance tests
|  | 70 | Product fails no more than 25% of customer happy path acceptance tests and fails no more than 50% of sad path acceptance tests
|  | 60 | Product fails more than 25% of customer happy path acceptance tests or fails more than 50% of sad path acceptance tests
|  | 50 | Deliverables show lack of comprehension of concepts, or are incomplete
Grading rubic: Process Aspect
|  | 100 | Exceptional job worthy of being used as an example of superior work
|  | 95 | Process has insignificant exceptions
|  | 90 | Process has multiple minor exceptions
|  | 85 | Process has exceptions that obsure activity verification
|  | 80 | Process has exceptions with data that affect the current project
|  | 75 | Process has exceptions that suggest lack of comprehension of concepts
|  | 70 | Process has exceptions that bring into question the validity of the data
|  | 65 | Process has exceptions suggesting it wasn't followed.
|  | 50 | Deliverables are incomplete
Quality checks |  |  | changes from the previous assignment are in red
General
Are all regions highlighted in yellow appropriately complete?
Does the workbook reflect a faithful record of information?
Has this assignment been uploaded as specified by the assignment description?
Project Plan Summary
Was the planned information determined before development and not altered after development?
Is planned time expressed in minutes?
Do LOC counts address production code (and exclude test code)?
Is the actual line count calculated according to the counting standard?
Time Recording Log
Does the log reflect a faithful record of time spent?
Do no times span midnight?
Does the log reflect the activities in the specified process?
Is post mortem the final phase?
Does the time recording log reflect the your lifecycle?
Change Log
Is each change accompanied by a description in the "comment" field?
Are changes recorded against the appropriate phase in which they were injected and removed?
Does the "removed" count equal the "injected" count? If not, is the rational documented in the "lessons learned" tab?
Are the dates and times in the change log consistent with the dates and times in the time recording log?
Acceptance Report
Do actual results support expected results?
Do actual results marked as "Passed with issues" include a comment?
Source Code
Does the code reflect the coding standard?
Will the code compile without change?
Does the production code contain any packages that aren't part of the customer's production environment.
Does the code take into consideration specified error conditions?
Does the code fulfill the requirements?
Does the code follow the prescribed directory format (i.e., test, sandbox)?
Historical Data
Is the historical data complete?
Have previously noted problems in process measurements been corrected?
Deliverables
Has the spreadsheet been uploaded to Canvas?
Has all the code been pushed to GitHub?
Is test code in a separate folder?
Will the test code work without modification?
Does the git respository reflect commits at the specified process points?
Does the "Assessment" tab include your name, your AU username, etc.
Review
Did you construct your review checklist during the planning phase?
Did you list all tests that failed when the customer performed his/her acceptance tests?
Are checklist items tailored to tests and not production code?
Did you determine the root cause of what your tests missed that your customer's tests caught?
Does your checklist contain more than "mom and apple pie" items?
Are checklist items answerable in "yes" or "no" terms?
Refactor
Is code free of the following bad smells: duplicate code, long methods, long classes
temporary variables, useless comments, coding standard violations?
Scenario
Were the scenarios constructed during the analysis phase (and not changed later)?
Does each scenario describe as fully as possible the interaction with the software under construction?
Are the actors correctly identified?
Are suitably understandable examples given?
Are events and responses directly observable?
Architecture
Was the architecture determined before construction (and not changed later)?
Does the architecture reflect a solid initial understanding of the solution?
Does the architecture show all components required for the solution (with the exception of system built-in components)?
Are collaborators specified correctly?
Do functionally-decomposed components have only one operation? Has the operation been given the component name?
Are component operations given names to suggest their behavior?
Does the architecture exhibit "good" design characteristics, such as appropriate levels of coupling, cohesion, etc.?
Estimate
Does each component denoted by a CRC card appear in the estimate as either base code or new component?
Do the base components and the new comopnents reflect the architecture?
Are the base components and new components sized according to historical proxies?
Is a rationale provided if either the LOCp and/or Ep are overridden?
Does the value of LOCa reflect effort expended on creating, adding, or modifying production code?
Is actual LOC data recorded at post mortem time?
Iterations
Is more than one iteration planned?
Does the WBS list all iterations?
Is the overall estimate of time in the WBS consistent with the calculated effort?
Are the planned completion dates of iterations in the WBS consistent with the calendar?
Are planned times recorded from the start of the calendar through the end of the project?
Does the calendar corroborate the WBS, and visa versa?
Construction
Did you follow the design -> test(failure) -> code -> test(success) -> clean up (if necessary) -> repeat pattern?
Are all unit tests written so that passing the test satisifies requirements?
Are unit tests written to the level of boundary value analysis?
Is there at least one test suite which, when run, exercises the entire production code base?
Does your code pass all test cases?

## Historical Data (hidden)
Constants |  |  |  |  | 0
Start date: | 36526 |  | Grades: | AA | 1
End date: | 73051 |  |  | A | 0.95
Phases: | Analyze | Identifying customer needs |  | AB | 0.9
| Architect | High-level design |  | B | 0.85
| Plan project | Determine actions/effort for project duration |  | BC | 0.8
| Plan iteration | Determine actions/effort this iteration |  | C | 0.75
| Construct | Low-level design, coding, unit testing |  | CD | 0.7
| Refactor | Restructure internal design |  | D | 0.65
| Review | Examine test code for risk mitigation |  | F | 0.5
| Integration test | End-to-end test of components to date
| Repattern | Restructure external design
| Postmortem | Capture post-development statistics
| Sandbox | Prove ideas, try concepts
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful
| Test syntax | Syntax flaws in the test code |  | 6
| Test logic | Logic flaws in the test code |  | 7
| Test interface | Flaws in the interface of a component of the test code |  | 8
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0
Y/N: | Yes |  |  | Passed | 0
| No |  |  | Passed with issues | 0
Proxy Types: | - |  |  | Failed | Base
| Calculation |  |  | Not tested | New
| Data |  |  | Not applicable | Reusable
I/O
Logic
Sizes: | VS | S | M | L | VL
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999
mid | -2 | -1 | 0 | 1 | 2
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5
| 0 | 0 | 0 | 0
Historical Data
Current Assignment: |  | Assignment 6 | CAAssignment 6.xls
Immediate Past Assignment: |  | Assignment6 | Assignment6
As of the end of |  |  | Assignment6
|  | Assignment6 | Assignment6 | All previous
Program Size (LOC) |  | LOCp | LOCa | LOCa
Base code LOC count
Lines deleted from Base
Lines modified from Base
Lines added to Base
Reused lines
New lines of production code
Component Count |  | Plan | Actual | Actual to Date
Reused components |  |  |  | 0
Modified components |  |  |  | 0
New components |  |  |  | 0
|  | Assignment6 | Assignment6 | All previous
Time In Phase (minutes) |  | Ep | Ea | Ea | To Date %
Analyze |  |  |  |  | 0%
Architect |  |  |  |  | 0%
Plan project |  |  |  |  | 0%
Plan iteration |  |  |  |  | 0%
Construct |  |  |  |  | 0%
Refactor |  |  |  |  | 0%
Review |  |  |  |  | 0%
Integration test |  |  |  |  | 0%
Repattern |  |  |  |  | 0%
Postmortem |  |  |  |  | 0%
Sandbox |  |  |  |  | 0%
TOTAL |  |  |  | 0 | 0%
All previous
Changes traced to the activities below: |  |  |  | changes | To Date %
Analyze |  |  |  |  | 0%
Architect |  |  |  |  | 0%
Plan project |  |  |  |  | 0%
Plan iteration |  |  |  |  | 0%
Construct |  |  |  |  | 0%
Refactor |  |  |  |  | 0%
Review |  |  |  |  | 0%
Integration test |  |  |  |  | 0%
Repattern |  |  |  |  | 0%
Postmortem |  |  |  |  | 0%
Sandbox |  |  |  |  | 0%
TOTAL |  |  |  | 0 | 0%
App previous
Changes implemented in the activities below: |  |  |  | changes | To Date %
Analyze |  |  |  |  | 0%
Architect |  |  |  |  | 0%
Plan project |  |  |  |  | 0%
Plan iteration |  |  |  |  | 0%
Construct |  |  |  |  | 0%
Refactor |  |  |  |  | 0%
Review |  |  |  |  | 0%
Integration test |  |  |  |  | 0%
Repattern |  |  |  |  | 0%
Postmortem |  |  |  |  | 0%
Sandbox |  |  |  |  | 0%
TOTAL |  |  |  | 0 | 0%
Size Matrix (LOC/Method)
| Lower | Mid | Upper
VS
S
M
L
VL
Project History
| New and Changed LOC |  |  | Effort
Project Name | Raw LOC | Planned LOC | Actual LOC | Estimated Time | Actual Time | LOCa/LOCr | Ea/LOCa
1.xls | 0 |  |  |  |  | 0 | 0
CA02 | 0 |  |  |  |  | 0 | 0
3.xls | [5 empty] | 0 | 0
CA04 | 0 |  |  |  |  | 0 | 0
CA05 |  | 0 | 0 | 0 | 0 | 0 | 0
Project Trends
Productivity= |  | LOC/hr
Average size= |  | LOC/method
Component History
Component Name |  | Total LOC | Method Count | Type | Size | LOC/method | ln(LOC/meth)
dispatch |  |  |  | Logic | -
|  |  |  | - | -
|  |  |  | - | - |  |  | `
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
[6 empty] | Average= | 0
[6 empty] | Std= | 0
Note on C57: Estimate the number of new lines of code that provide new functionality to meet the specifications of this assignment.
Note on C61: Estimate of the number of previously-written components that require modification
Note on C62: Estimate of the number of entirely new components

## Acceptance
Start date: | 36526 |  |  | Grades: | AA | 1
End date: | 73051 |  |  |  | A | 0.95
Phases: | Analyze |  | Identifying customer needs |  | AB | 0.9
| Architect |  | High-level design |  | B | 0.85
| Plan project |  | Determine actions/effort for project duration |  | BC | 0.8
| Plan iteration |  | Determine actions/effort this iteration |  | C | 0.75
| Construct |  | Low-level design, coding, unit testing |  | CD | 0.7
| Refactor |  | Restructure internal design |  | D | 0.65
| Review |  | Examine test code for risk mitigation |  | F | 0.5
| Integration test |  | End-to-end test of components to date
| Repattern |  | Restructure external design
| Postmortem |  | Capture post-development statistics
| Sandbox |  | Prove ideas, try concepts
Defect Types: | Requirements Change |  | Changes to requirements | Iteration | NA | did not follow
| Requirements Clarification |  | Clarifications to requirements |  | 1 | very painful
| Product syntax |  | Syntax flaws in the deliverable product |  | 2 | painful
| Product logic |  | Logic flaws in the deliverable product |  | 3 | neutral
| Product interface |  | Flaws in the interface of a component of the deliverable product |  | 4 | helpful
| Product checking |  | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful
| Test syntax |  | Syntax flaws in the test code |  | 6
| Test logic |  | Logic flaws in the test code |  | 7
| Test interface |  | Flaws in the interface of a component of the test code |  | 8
| Test checking |  | Flaws with boundary/type checking within a component of the test code |  | 9
| Bad Smell |  | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0
Y/N: | Yes |  |  |  | Passed | 0
| No |  |  |  | Passed with issues | 0
Proxy Types: | - |  |  |  | Failed | Base
| Calculation |  |  |  | Not tested | New
| Data |  |  |  | Not applicable | Reusable
I/O
Logic
Sizes: | VS |  | S | M | L | VL | VS
upper | -1.5 |  | -0.5 | 0.5 | 1.5 | 99999 | S
mid | -2 |  | -1 | 0 | 1 | 2 | M
lower | 0 |  | -1.5 | -0.5 | 0.5 | 1.5 | L
| 0 |  | 0 | 0 | 0 |  | VL
Acceptance Test Report
Use this worksheet to record tests that, if passed, tell you that your software is complete. It is not a chronology, so do not list a history of tests. List only tests that are directly linked to requirements (in other words, do not list tests for methods or components that you create over and above what is required to fulfill the specified interface definition -- these tests will appear in your individual unit test files). Write the expected results at planning time. Modify if necessary later. Don’t write actual results in advance.
Requirements:
from iteration 0
from iteration 1
from iteration 2
from iteration 3
from iteration 4
from iteration 5
from iteration 6
from iteration 7
from iteration 8
Requirement | Test Description | Test | Expected Results |  | Actual Results | Issues
from iteration 6 | Produce the rotations needed to solve a fully solved cube | localhost:8080/rubik?op=solve&cube=gggggggggrrrrrrrrrbbbbbbbbbooooooooowwwwwwwwwyyyyyyyyy | {'rotations': '', 'status': 'ok', 'token': 'some_token'} |  | Passed
from iteration 6 | Produce the rotations needed to solve an invalid cube | localhost:8080/rubik?op=solve&cube=rrrrrrrrrbbbbbbbbbooooooooowwwwwwwwwyyyyyyyyy | {'status': 'error: invalid cube'} |  | Passed
from iteration 6 | Produce the rotations needed to solve a completely unsolved cube | localhost:8080/rubik?op=solve&cube=orwbrrbwrrrggggbowyywooygwgbbgobrwyyogrwyyywbogybwbroo | {'rotations': 'UfuRBUruFFRRLLBBuluuLUluLUURurLulUULUlUruuRBuburURuulULUFufUfUFURurLulubUBuLulubUBBuburURuFRUruRUrufURUrURUUruRUrURUUrufUBuFUUbUBUUbLLUfBLLbFUUfBLLbFULL', 'status': 'ok', 'token': 'some_token'} |  | Passed
from iteration 6 | Produce the rotations needed to solve a cube with fully solved down and middle layers and top face | localhost:8080/rubik?op=solve&cube=grbrrrrrrrboggggggbggoooooooorbbbbbbyyyyyyyyywwwwwwwww | {'rotations': 'lURuLUUrURUUrUUlURuLUUrURUUrLLUfBLLbFUUfBLLbFULL', 'status': 'ok', 'token': 'some_token'} |  | Passed
from iteration 6 | Produce the rotations needed to solve a cube with down and middle layers solved | localhost:8080/rubik?op=solve&cube=oyyrrrrrrgyrgggggggyyoooooobyybbbbbbrrygybboowwwwwwwww | {'rotations': 'FRUrufuuFRUruRUrufRUrURUUrURUrURUUrLLUfBLLbFULL', 'status': 'ok', 'token': 'some_token'} |  | Passed
from iteration 6 | Produce the rotations needed to solve a cube with down layer solved | localhost:8080/rubik?op=solve&cube=gryybgbbbbbryrgrrrgbyogygggobyrooooobryoyyogrwwwwwwwww | {'rotations': 'uulULUFufufUFURurBuburURubUBULulBuburURuFRUrufURUrURUUruRUrURUUrURUrURUUrubUFuBUUfUFUUf', 'status': 'ok', 'token': 'some_token'} |  | Passed
Note on A61: Establish traceability between the tests and requirements.
Note on B61: Defines observable tests that have quantifiable resutls.
Note on C61: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Please put the URL of your microservice here (as appropriate)
Note on D61: Specifies the result that that the test is anticipated to produce.
Note on F61: Defines the result of running the test in relation to the expected result.
Note on G61: Required whenthe actual result is "Passed with issues"; optional otherwise. An "issue" is a side-effect that is not part of the specified test.

## Review
Review
Standards
Start date: |  | 2000-01-01 | Grades:
End date: |  | 2020-01-01
Phases: |  | Analysis
Architecture
Planning
Construction
Refactoring
Review
Integration Test
Postmortem
Sandbox
Defect Types: |  | Documentation | Iteration
|  | Build | 0
|  | Product syntax | 1
|  | Product logic | 2
|  | Product interface | 3
|  | Product checking | 4
|  | Test syntax | 5
|  | Test logic | 6
|  | Test interface | 7
|  | Test checking | 8
|  | Bad Smell | 9
Y/N: |  | Yes | 10
No
Proxy Types: |  | Calculation
Data
I/O
Logic
Sizes: |  | VS | passed
|  | S | failed
M
L
VL
Use this worksheet to record when you were notified by the user of an acceptance test failure, what was missing in your test code, and what check you need to put in place to ensure similar omissions don't happen again in the future.
| Iteration | Failed acceptance test from earlier iteration |  | What did your test code miss? | Resulting test-oriented checklist item | Number of times this item detected a defect during review
| 5 | Iteration 3: localhost:8080/rubik?op=solve&cube=yrooyrwrrbygwbygwwwbggroywbbwwbwyyroygroobogrrbboggoyg |  | My test code missed a situation where an infinite loop can occur with certain configurations of the up surface of the cube. | Test the following up surface configuration: up cross solved and two adjacent corners are solved/or two diagonal corners are solved. For example cube is yoyggggggggroooooogrobbbbbbbbrrrrrrryyyyyybyowwwwwwwww or oggggggggyoooooooobrybbbbbbbbgrrrrrrryyyyyyyrwwwwwwwww or similar configurations | 0
| 5 | Iteration 3: localhost:8080/rubik?op=solve&cube=ogobooyrbwbgwwyggyrworborbwrwwyrrywrgbbgyygryoowygobgb |  | My test code missed a situation where an infinite loop can occur with certain configurations of the up surface of the cube. | Test the following up surface configuration: up cross solved and two adjacent corners are solved/or two diagonal corners are solved. For example cube is yoyggggggggroooooogrobbbbbbbbrrrrrrryyyyyybyowwwwwwwww or oggggggggyoooooooobrybbbbbbbbgrrrrrrryyyyyyyrwwwwwwwww or similar configurations | 0
| 5 | Iteration 3: localhost:8080/rubik?op=solve&cube=owygryowygwrryorbbbggyobgwwyrygborgbrygbwrwyowowrgobbo |  | My test code missed a situation where an infinite loop can occur with certain configurations of the up surface of the cube. | Test the following up surface configuration: up cross solved and two adjacent corners are solved/or two diagonal corners are solved. For example cube is yoyggggggggroooooogrobbbbbbbbrrrrrrryyyyyybyowwwwwwwww or oggggggggyoooooooobrybbbbbbbbgrrrrrrryyyyyyyrwwwwwwwww or similar configurations | 0
| 5 | Iteration 4: localhost:8080/rubik?op=solve&cube=bgrrggwwwboyyryrboooowwyrgwrwgbyoyoygygbbgyrgbrbworobw |  | My test code missed a situation where an infinite loop can occur with certain configurations of the up surface of the cube. | Test the following up surface configuration: up cross solved and two adjacent corners are solved/or two diagonal corners are solved. For example cube is yoyggggggggroooooogrobbbbbbbbrrrrrrryyyyyybyowwwwwwwww or oggggggggyoooooooobrybbbbbbbbgrrrrrrryyyyyyyrwwwwwwwww or similar configurations | 0
| 5 | Iteration 5: localhost:8080/rubik?op=solve&cube=rrbbogbrwgyybrobywrborwoyworggyboygogyowgrwwwggyoywbbr |  | My test code missed a situation where an infinite loop can occur with certain configurations of the up surface of the cube. | Test the following up surface configuration: up cross solved and two adjacent corners are solved/or two diagonal corners are solved. For example cube is yoyggggggggroooooogrobbbbbbbbrrrrrrryyyyyybyowwwwwwwww or oggggggggyoooooooobrybbbbbbbbgrrrrrrryyyyyyyrwwwwwwwww or similar configurations | 0
| 5 | Iteration 5: localhost:8080/rubik?op=solve&cube=wrborwowwgwrrwgogbbbgooygrrygrogbgryowwbyoygowybbbyyyr |  | My test code missed a situation where an infinite loop can occur with certain configurations of the up surface of the cube. | Test the following up surface configuration: up cross solved and two adjacent corners are solved/or two diagonal corners are solved. For example cube is yoyggggggggroooooogrobbbbbbbbrrrrrrryyyyyybyowwwwwwwww or oggggggggyoooooooobrybbbbbbbbgrrrrrrryyyyyyyrwwwwwwwww or similar configurations | 0
| 5 | Iteration 5: localhost:8080/rubik?op=solve&cube=owgowbogywywoorgwwgrbbbroggogyogyrwyrwrbybboywrbyrgbyr |  | My test code missed a situation where an infinite loop can occur with certain configurations of the up surface of the cube. | Test the following up surface configuration: up cross solved and two adjacent corners are solved/or two diagonal corners are solved. For example cube is yoyggggggggroooooogrobbbbbbbbrrrrrrryyyyyybyowwwwwwwww or oggggggggyoooooooobrybbbbbbbbgrrrrrrryyyyyyyrwwwwwwwww or similar configurations | 0

## Map (hidden)
Sceneario-Component Map
X
Component Names:
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!

## Architecture - Pre
Architecture
Use this worksheet to describe components required to implement the specifications. List new components and base components. Do not include extraneous components. | Use this worksheet to describe components required to implement the specifications. List new components and base components. Do not include extraneous components.
Standards
| Start date: | 2000-01-01
| End date: | 2010-01-01
| Phases: | Planning
Design
Design Review
Code
Code Review
Compile
Test
Postmortem
| Defect Types: | Documentation
Syntax
Build, Package
Assignment
Interface
Checking
Data
Function
System
Environment
| Y/N: | Yes
No
| Component Types: | Calculation
Data
I/O
Logic
| Design Approaches: | Object-oriented
Functional
| Sizes: | VS
S
M
L
VL
| Duration: | LOCe x T
LOCa x T
Productivity
1 | Component Name: | _solve
| Design Approach: | Functional
| Parent Component: | None
Attributes (optional):
| Component Type: | Logic
| Collaborators: | _isCubeValid, _solveDaisyAndDownCross, _solveDownCorners, _solveMiddleLayer, _solveUpCross, _solveUpFace, _solveUpCorners, _solveUpMiddlePieces
| Operations: | solve rubik's cube
2 | Component Name: | _solveUpCorners
| Design Approach: | Functional
| Parent Component: | None
Attributes (optional):
| Component Type: | Logic
| Collaborators: | _rotatePiece
| Operations: | solve up corners of rubik's cube
3 | Component Name: | _solveUpMiddlePieces
| Design Approach: | Functional
| Parent Component: | None
Attributes (optional):
| Component Type: | Logic
| Collaborators: | _rotatePiece
| Operations: | solve up middle pieces of rubik's cube
4 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
5 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
6 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
7 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
8 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
9 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
10 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Note on B43: Identifying name for this design class or function.
Note on B44: Indicate if this design component will follow an object-oriented approach or a functional approach.
Note on B45: Superclass of this design component. Leave blank if no superclass.
Note on B46: Attributes (e.g., public fields, public constants) associated with this design component. OPTIONAL
Note on B47: Standard category of the design component.
Note on B48: List components that this component calls upon to fulfill its purpose.
Note on B49: Description of the operations of this design component. If your are taking an object-oriented approach, list the methods associated with this object in the "operation" column. If you are taking a functional approach, list the component name in the "operation" column. Note: an object-oriented approach may result in zero or more operations; a functional approach will have only one operation listed.

## Estimation
Size Estimate
Use this worksheet to estimate effort for the current iteration.
Constants |  |  |  |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Start date: | 36526 |  | Grades: | AA | 1 | 0 | 44889 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
End date: | 73051 |  |  | A | 0.95 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Phases: | Analyze | Identifying customer needs |  | AB | 0.9 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Architect | High-level design |  | B | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Plan project | Determine actions/effort for project duration |  | BC | 0.8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Plan iteration | Determine actions/effort this iteration |  | C | 0.75 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Construct | Low-level design, coding, unit testing |  | CD | 0.7 | 44883 | 0 | 0 | AM | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Refactor | Restructure internal design |  | D | 0.65 | 44882 | 1 | 5 | PM | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Review | Examine test code for risk mitigation |  | F | 0.5 | 44881 | 2 | 10 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Integration test | End-to-end test of components to date |  |  |  | 44880 | 3 | 15 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Repattern | Restructure external design |  |  |  | 44879 | 4 | 20 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Postmortem | Capture post-development statistics |  |  |  | 44878 | 5 | 25 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Sandbox | Prove ideas, try concepts |  |  |  | 44877 | 6 | 30 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
[6 empty] | 44876 | 7 | 35 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
[6 empty] | 44875 | 8 | 40 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
[6 empty] | 44874 | 9 | 45 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
[6 empty] | 44873 | 10 | 50 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow | 44872 | 11 | 55 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful | 44871 | 12 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful | 44870 | 13 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral | 44869 | 14 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful | 44868 | 15 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful | 44867 | 16 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Test syntax | Syntax flaws in the test code |  | 6 |  | 44866 | 17 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Test logic | Logic flaws in the test code |  | 7 |  | 44865 | 18 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Test interface | Flaws in the interface of a component of the test code |  | 8 |  | 44864 | 19 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9 |  | 44863 | 20 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0 | 44862 | 21 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Y/N: | Yes |  |  | Passed | 0 | 44861 | 22 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| No |  |  | Passed with issues | 0 | 44860 | 23 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Proxy Types: | - |  |  | Failed | Base | 44859 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Calculation |  |  | Not tested | New | 44858 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Data |  |  | Not applicable | Reusable | 44857 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| I/O |  |  |  |  | 44856 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Logic |  |  |  |  | 44855 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
[6 empty] | 44854 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Sizes: | VS | S | M | L | VL | VS | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999 | S | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
mid | -2 | -1 | 0 | 1 | 2 | M | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5 | L | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 |  | VL | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
<-- Mandatory |  | ✔ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Component History
Component Name |  | Total LOC | Method Count | Type | LOC/method | ln(LOC/meth) |  | Size
_rotate |  | 24 | 1 | Logic | 24 | 3.1781 |  | M
_solve |  | 35 | 1 | Logic | 35 | 3.5553 |  | L
_solveDaisyAndDownCross |  | 29 | 1 | Logic | 29 | 3.3673 |  | M |  |  | `
_solveDownCorners |  | 36 | 1 | Logic | 36 | 3.5835 |  | L
_solveMiddleLayer |  | 36 | 1 | Logic | 36 | 3.5835 |  | L
_solveUpCross |  | 22 | 1 | Logic | 22 | 3.091 |  | M
_solveUpFace |  | 29 | 1 | Logic | 29 | 3.3673 |  | M
_solveDaisy |  | 24 | 1 | Logic | 24 | 3.1781 |  | M
_solveDownCross |  | 20 | 1 | Logic | 20 | 2.9957 |  | S
_solveBottomDaisyPiece |  | 32 | 1 | Logic | 32 | 3.4657 |  | L
_solveRightDaisyPiece |  | 31 | 1 | Logic | 31 | 3.434 |  | M
_solveLeftDaisyPiece |  | 30 | 1 | Logic | 30 | 3.4012 |  | M
_solveTopDaisyPiece |  | 29 | 1 | Logic | 29 | 3.3673 |  | M
_putBottomDaisyInDownCross |  | 16 | 1 | Logic | 16 | 2.7726 |  | S
_putRightDaisyInDownCross |  | 16 | 1 | Logic | 16 | 2.7726 |  | S
_putLeftDaisyInDownCross |  | 16 | 1 | Logic | 16 | 2.7726 |  | S
_putTopDaisyInDownCross |  | 16 | 1 | Logic | 16 | 2.7726 |  | S
_solveFrontLeftDownCorner |  | 38 | 1 | Logic | 38 | 3.6376 |  | L
_solveFrontRightDownCorner |  | 35 | 1 | Logic | 35 | 3.5553 |  | L
_solveBackLeftDownCorner |  | 32 | 1 | Logic | 32 | 3.4657 |  | L
_solveBackRightDownCorner |  | 29 | 1 | Logic | 29 | 3.3673 |  | M
_sovleFrontLeftMiddlePiece |  | 30 | 1 | Logic | 30 | 3.4012 |  | M
_solveFrontRightMiddlePiece |  | 28 | 1 | Logic | 28 | 3.3322 |  | M
_solveBackLeftMiddlePiece |  | 26 | 1 | Logic | 26 | 3.2581 |  | M
_solveBackRightMiddlePiece |  | 24 | 1 | Logic | 24 | 3.1781 |  | M
_findDownCorner |  | 19 | 1 | Logic | 19 | 2.9444 |  | S
_findMiddleLayerPiece |  | 21 | 1 | Logic | 21 | 3.0445 |  | S
_rotatePiece |  | 7 | 1 | Logic | 7 | 1.9459 |  | VS
_isDirValid |  | 15 | 1 | Logic | 15 | 2.7081 |  | VS
_rotateCube |  | 32 | 1 | Logic | 32 | 3.4657 |  | L
_rotateFrontClockwise |  | 33 | 1 | Logic | 33 | 3.4965 |  | L
_rotateFrontCounterClockwise |  | 33 | 1 | Logic | 33 | 3.4965 |  | L |  |  | `
_rotateRightClockwise |  | 33 | 1 | Logic | 33 | 3.4965 |  | L
_rotateRightCounterClockwise |  | 33 | 1 | Logic | 33 | 3.4965 |  | L
_rotateBackClockwise |  | 33 | 1 | Logic | 33 | 3.4965 |  | L
_rotateBackCounterClockwise |  | 33 | 1 | Logic | 33 | 3.4965 |  | L
_rotateLeftClockwise |  | 33 | 1 | Logic | 33 | 3.4965 |  | L
_rotateLeftCounterClockwise |  | 33 | 1 | Logic | 33 | 3.4965 |  | L
_rotateUpClockwise |  | 33 | 1 | Logic | 33 | 3.4965 |  | L
_rotateUpCounterClockwise |  | 33 | 1 | Logic | 33 | 3.4965 |  | L
_rotateDownClockwise |  | 33 | 1 | Logic | 33 | 3.4965 |  | L
_rotateDownCounterClockwise |  | 33 | 1 | Logic | 33 | 3.4965 |  | L
_verfiy |  | 12 | 1 | Logic | 12 | 2.4849 |  | VS
_isCubeValid |  | 24 | 1 | Logic | 24 | 3.1781 |  | M
-
-
-
-
-
-
-
-
-
-
-
-
-
-
[5 empty] | average | 3.2633
[5 empty] | std | 0.35105
Size Matrix (LOC/Method)
| Lower | Mid | Upper
VS | 1 | 1 | 15.4
S | 15.4 | 18.4 | 21.9
M | 21.9 | 26.1 | 31.1
L | 31.1 | 37.1 | 44.2
VL | 44.2 | 52.7 | infinity
Project History
| New and Changed LOC |  |  | Effort
Iteration | Raw LOC | Planned LOC | Actual LOC | Estimated Time | Actual Time | LOCa/LOCr |  | Ea/LOCa
3 | 300 | 300 | 200 | 700 | 1100 | 0.66667 |  | 5.5
4 | 200 | 200 | 167 | 600 | 565 | 0.835 |  | 3.3832
5 | 68 | 50 | 73 | 227 | 237 | 1.0735 |  | 3.2466
6 | [5 empty] | 0 |  | 0
Project Trends
Productivity= | 13.8801 | LOC/hr
Average size= |  | LOC/method
|  |  | Estimated | [10 empty] | Actual
|  |  | Changes to existing code |  |  |  |  | New code | [5 empty] | Changes to existing code |  |  |  |  | New code
Component | Type | Relative Size | Number of LOC modified in base | Number of LOC added to base | Number of LOC deleted from base | Number of base LOC contributing to effort |  | Number of new methods added | LOC/Method | Number of new LOC contributing to effort | Total number of LOC contributing to effort (LOCr) | Total Tasks |  | Number of LOC modified in base | Number of LOC added to base | Number of LOC deleted from base | Number of base LOC contributing to effort |  | Number of new methods added | LOC/Method | Number of new LOC contributing to effort | Total number of LOC contributing to effort (LOCa) | Total tasks | Is this component reusable?
_solve | Base | L | 0 | 4 | 0 | 4 |  | 0 | 37.1 | 0 | 4 | 1 |  | 0 | 4 | 0 | 4 |  | 0 |  | 0 | 4 | 1 | No
_solveUpCorners | New | L | 0 | 0 | 0 | 0 |  | 1 | 37.1 | 37.1 | 37.1 | 1 |  | 0 | 0 | 0 | 0 |  | 1 | 39 | 39 | 39 | 1 | Yes
_solveUpMiddlePieces | New | M | 0 | 0 | 0 | 0 |  | 1 | 26.1 | 26.1 | 26.1 | 1 |  | 0 | 0 | 0 | 0 |  | 1 | 27 | 27 | 27 | 1 | Yes
[6 empty] | 0 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
[6 empty] | 0 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
[6 empty] | 0 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
[6 empty] | 0 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
[6 empty] | 0 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
[6 empty] | 0 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
[6 empty] | 0 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
[6 empty] | 0 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
[6 empty] | 0 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
[6 empty] | 0 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
[6 empty] | 0 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
[6 empty] | 0 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
[6 empty] | 0 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
[6 empty] | 0 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
[6 empty] | 0 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
[6 empty] | 0 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
[6 empty] | 0 |  |  |  | 0 | 0 | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0
LOC Totals |  |  | 0 | 4 | 0 | 4 |  | 2 |  | 63.2 | 67.2 | 3 |  | 0 | 4 | 0 | 4 | 0 | 2 |  | 66 | 70 | 3
Size Calculation | [14 empty] | Actual: | LOCa= | 70
| LOCr = | 67.2
| LOCa/LOCr= | 0.77465
| LOCp= | 53
|  | 0.96394 | High
Effort Calculation
| Ea/LOCa= | 4.3227
| Prod= | 14
| Ep= | 229.1045
0
|  | 0 | Low
Estimation: | LOCr= |  | 67.2
| LOCp= |  | 53
| Ep= |  | 229
| Rationale for override: |  | Not applicable

## ArcEstimation (hidden)
Size Estimate
Standards
Start date: | 2000-01-01 |  |  | Grades: | AA
End date: | 2020-01-01 |  |  |  | A
Phases: | Planning |  |  |  | AB
| Architecture |  |  |  | B
| Construction |  |  |  | BC
| Refactoring |  |  |  | C
| Integration Test |  |  |  | CD
| Review |  |  |  | D
| Sandbox |  |  |  | F
Postmortem
Defect Types: | Documentation
| Build |  |  | Type | Event
| Product syntax |  |  |  | Response
| Product logic |  |  | Origin | Test Component
| Product interface |  |  |  | Blackbox
| Product checking |  |  |  | User
| Test syntax |  |  |  | External Component (specify)
| Test logic |  |  | Op Spec type | User
| Test interface |  |  |  | Interface
Test checking
Y/N: | Yes
No
Proxy Types: | Calculation
Data
I/O
Logic
Metaphysics: | Object-oriented
Functional
Sizes: | VS
S
M
L
VL
Duration: | LOCe x T
LOCa x T
Productivity
| Estimated |  |  |  |  | Actual
Base Components | Base LOC | Deleted LOC | Modified LOC | Added LOC |  | Base LOC | Deleted LOC | Modified LOC | Added LOC
Totals | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Estimated |  |  |  |  | Actual
New Components | Method Count | LOCr | Reuseable? |  |  | Method Count | LOCa | Reusable?
Totals |  | 0 |  |  |  |  | 0
Actual
Reused Parts | LOC
Totals | 0
Size Calculation
#REF!
0
#REF!
|  | 0 | Low
Effort Calculation
0
#REF!
#REF!
#REF!
|  | 0 | Low
Estimation | LOCr= |  | 0
| LOCp= |  | 0 |  |  | LOCa= | 0
| Ep= |  | 0
Rationale for override:
Note on G66: Indicate only new methods and LOC that resulted from effort. Do not count items that were previously base code and were refactored into new components.

## Schedule (hidden)
Iterations
Standards
Start date: | 2000-01-01
End date: | 2025-01-01
Phases: | Planning
Design
Design Review
Code
Code Review
Compile
Test
Postmortem
Documentation
Syntax
Defect Types: | Build, Package
Assignment
Interface
Checking
Data
Function
System
Environment
Y/N: | Yes
No
Proxy Types: | Calculation
Data
I/O
Logic
|  |  | estimation methods | A
Sizes: | VS |  |  | B
| S |  |  | C
| M |  |  | D
L
VL
Duration: | LOCe x T
LOCa x T
Productivity
Component-Iteration Map
| Component | Number of Tasks
| _solve | 1
| _solveUpCorners | 1
| _solveUpMiddlePieces | 1
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| Number of tasks: | 3
| Effort per task: | 76.3333
WBS
| Iteration Number | Planned Effort (minutes) | Planned Velocity | Effort per task
1
2
3
4
5
| 6 | 229 | 3 | 76.3333
7
8
9
10
Calendar
|  |  | Planned |  |  |  |  | Actual
| Day # | Date | Available Minutes | Cumulative Minutes | Planned Velocity | Cumulative Planned Velocity | Planned Completion | Available Minutes | Cumulative Minutes | Earned Velocity | Cumulative Earned Velocity
| 1 | 2022-10-31 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 2 | 2022-11-01 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 3 | 2022-11-02 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 4 | 2022-11-03 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 5 | 2022-11-04 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 6 | 2022-11-05 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 7 | 2022-11-06 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 8 | 2022-11-07 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 9 | 2022-11-08 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 10 | 2022-11-09 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 11 | 2022-11-10 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 12 | 2022-11-11 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 13 | 2022-11-12 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 14 | 2022-11-13 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 15 | 2022-11-14 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 16 | 2022-11-15 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 17 | 2022-11-16 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 18 | 2022-11-17 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 19 | 2022-11-18 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 20 | 2022-11-19 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 21 | 2022-11-20 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 22 | 2022-11-21 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 23 | 2022-11-22 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 24 | 2022-11-23 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 25 | 2022-11-24 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 26 | 2022-11-25 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 27 | 2022-11-26 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 28 | 2022-11-27 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 29 | 2022-11-28 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 30 | 2022-11-29 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 31 | 2022-11-30 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 32 | 2022-12-01 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 33 | 2022-12-02 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 34 | 2022-12-03 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 35 | 2022-12-04 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 36 | 2022-12-05 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 37 | 2022-12-06 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 38 | 2022-12-07 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 39 | 2022-12-08 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 40 | 2022-12-09 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 41 | 2022-12-10 |  | 0 | 0 | 0 |  |  | 0 |  | 0
| 42 | 2022-12-11 |  | 0 | 0 | 0 |  |  | 0 |  | 0
Formulas:
Planned Effort (minutes) = [Planned Effort (minutes), row below]-1
Planned Effort (minutes) = [Planned Effort (minutes), row above]+1

## Architecture - Post
Architecture
Use this worksheet to describe components required to implement the specifications. List new components and base components. Do not include extraneous components. | Use this worksheet to describe components required to implement the specifications. List new components and base components. Do not include extraneous components.
Standards
| Start date: | 2000-01-01
| End date: | 2010-01-01
| Phases: | Planning
Design
Design Review
Code
Code Review
Compile
Test
Postmortem
| Defect Types: | Documentation
Syntax
Build, Package
Assignment
Interface
Checking
Data
Function
System
Environment
| Y/N: | Yes
No
| Component Types: | Calculation
Data
I/O
Logic
| Design Approaches: | Object-oriented
Functional
| Sizes: | VS
S
M
L
VL
| Duration: | LOCe x T
LOCa x T
Productivity
1 | Component Name: | _solve
| Design Approach: | Functional
| Parent Component: | None
Attributes (optional):
| Component Type: | Logic
| Collaborators: | _isCubeValid, _solveDaisyAndDownCross, _solveDownCorners, _solveMiddleLayer, _solveUpCross, _solveUpFace, _solveUpCorners, _solveUpMiddlePieces
| Operations: | solve rubik's cube
2 | Component Name: | _solveUpCorners
| Design Approach: | Functional
| Parent Component: | None
Attributes (optional):
| Component Type: | Logic
| Collaborators: | _rotatePiece
| Operations: | solve up corners of rubik's cube
3 | Component Name: | _solveUpMiddlePieces
| Design Approach: | Functional
| Parent Component: | None
Attributes (optional):
| Component Type: | Logic
| Collaborators: | _rotatePiece
| Operations: | solve up middle pieces of rubik's cube
4 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
5 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
6 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
7 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
8 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
9 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
10 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Note on B43: Identifying name for this design class or function.
Note on B44: Indicate if this design component will follow an object-oriented approach or a functional approach.
Note on B45: Superclass of this design component. Leave blank if no superclass.
Note on B46: Attributes (e.g., public fields, public constants) associated with this design component. OPTIONAL
Note on B47: Standard category of the design component.
Note on B48: List components that this component calls upon to fulfill its purpose.
Note on B49: Description of the operations of this design component. If your are taking an object-oriented approach, list the methods associated with this object in the "operation" column. If you are taking a functional approach, list the component name in the "operation" column. Note: an object-oriented approach may result in zero or more operations; a functional approach will have only one operation listed.

## Plan (hidden)
Constants |  |  |  |  | 0
Start date: | 36526 |  | Grades: | AA | 1
End date: | 73051 |  |  | A | 0.95
Phases: | Analyze | Identifying customer needs |  | AB | 0.9
| Architect | High-level design |  | B | 0.85
| Plan project | Determine actions/effort for project duration |  | BC | 0.8
| Plan iteration | Determine actions/effort this iteration |  | C | 0.75
| Construct | Low-level design, coding, unit testing |  | CD | 0.7
| Refactor | Restructure internal design |  | D | 0.65
| Review | Examine test code for risk mitigation |  | F | 0.5
| Integration test | End-to-end test of components to date
| Repattern | Restructure external design
| Postmortem | Capture post-development statistics
| Sandbox | Prove ideas, try concepts
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful
| Test syntax | Syntax flaws in the test code |  | 6
| Test logic | Logic flaws in the test code |  | 7
| Test interface | Flaws in the interface of a component of the test code |  | 8
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0
Y/N: | Yes |  |  | Passed | 0
| No |  |  | Passed with issues | 0
Proxy Types: | - |  |  | Failed | Base
| Calculation |  |  | Not tested | New
| Data |  |  | Not applicable | Reusable
I/O
Logic
Sizes: | VS | S | M | L | VL
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999
mid | -2 | -1 | 0 | 1 | 2
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5
| 0 | 0 | 0 | 0
<-- Mandatory |  | ✔
Project Plan Summary
Use this worksheet to record how much production code you plan to write and the amount of time to write it. Record the actual size once the project is complete. The actual time will be calculated from the Time Log. Please note that you are not being evaluated on how close your planned values to your actual values.
Program Size (LOC) |  | Plan | Actual | To Date
Base code LOC count |  |  |  | 0
Lines deleted from Base |  |  |  | 0
Lines modified from Base |  |  |  | 0
Lines added to Base |  |  |  | 0
Reused lines |  |  |  | 0
New lines of production code |  |  |  | 0
Component Count |  | Plan | Actual | To Date
Reused components |  |  |  | 0
Modified components |  |  |  | 0
New components |  |  |  | 0
Time In Phase (minutes) |  | Plan | Actual | Actual to Date | Actual to Date %
Analyze |  |  | 15 | 15 | 8.108%
Architect |  |  | 10 | 10 | 5.405%
Plan project |  |  | 20 | 20 | 10.81%
Plan iteration |  |  | 0 | 0 | 0%
Construct |  |  | 90 | 90 | 48.65%
Refactor |  |  | 30 | 30 | 16.22%
Review |  |  | 10 | 10 | 5.405%
Integration test |  |  | 0 | 0 | 0%
Repattern |  |  | 0 | 0 | 0%
Postmortem |  |  | 10 | 10 | 5.405%
Sandbox |  |  | 0 | 0 | 0%
TOTAL |  |  | 185 | 185 | 100%
Changes Identified |  |  | Actual | Actual to Date | Actual to Date %
Analyze |  |  | 0 | 0 | 0%
Architect |  |  | 0 | 0 | 0%
Plan project |  |  | 0 | 0 | 0%
Plan iteration |  |  | 0 | 0 | 0%
Construct |  |  | 0 | 0 | 0%
Refactor |  |  | 0 | 0 | 0%
Review |  |  | 0 | 0 | 0%
Integration test |  |  | 0 | 0 | 0%
Repattern |  |  | 0 | 0 | 0%
Postmortem |  |  | 0 | 0 | 0%
Sandbox |  |  | 0 | 0 | 0%
TOTAL |  |  | 0 | 0 | 0%
Changes Implemented |  |  | Actual | Actual to Date | Actual to Date %
Analyze |  |  | 0 | 0 | 0%
Architect |  |  | 0 | 0 | 0%
Plan project |  |  | 0 | 0 | 0%
Plan iteration |  |  | 0 | 0 | 0%
Construct |  |  | 0 | 0 | 0%
Refactor |  |  | 0 | 0 | 0%
Review |  |  | 0 | 0 | 0%
Integration test |  |  | 0 | 0 | 0%
Repattern |  |  | 0 | 0 | 0%
Postmortem |  |  | 0 | 0 | 0%
Sandbox |  |  | 0 | 0 | 0%
TOTAL |  |  | 0 | 0 | 0%
Note on C48: Number of lines used from previously-written code
Note on C49: Estimate of the number of lines deleted from previously-written code
Note on C50: Estimated of the number of lines modified from previously-written code
Note on C51: Estimate of the number of lines added to previously-written code to bring it to the point where new functionality can be added
Note on C52: Count of the number of lines of reused source code
Note on C53: Estimate the number of new lines of production code that provide new functionality to meet the specifications of this assignment.
Note on C56: Number of reusable components that will be reused.
Note on C57: Estimate of the number of previously-delivered components that will be used.
Note on C58: Estimate of the number of new components to be built.
Note on C72: Estimate in minutes how much time you plan to expend on this assignment.

## Summary (hidden)
Constants |  |  |  |  | 0
Start date: | 36526 |  | Grades: | AA | 1
End date: | 73051 |  |  | A | 0.95
Phases: | Analyze | Identifying customer needs |  | AB | 0.9
| Architect | High-level design |  | B | 0.85
| Plan project | Determine actions/effort for project duration |  | BC | 0.8
| Plan iteration | Determine actions/effort this iteration |  | C | 0.75
| Construct | Low-level design, coding, unit testing |  | CD | 0.7
| Refactor | Restructure internal design |  | D | 0.65
| Review | Examine test code for risk mitigation |  | F | 0.5
| Integration test | End-to-end test of components to date
| Repattern | Restructure external design
| Postmortem | Capture post-development statistics
| Sandbox | Prove ideas, try concepts
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful
| Test syntax | Syntax flaws in the test code |  | 6
| Test logic | Logic flaws in the test code |  | 7
| Test interface | Flaws in the interface of a component of the test code |  | 8
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0
Y/N: | Yes |  |  | Passed | 0
| No |  |  | Passed with issues | 0
Proxy Types: | - |  |  | Failed | Base
| Calculation |  |  | Not tested | New
| Data |  |  | Not applicable | Reusable
I/O
Logic
Sizes: | VS | S | M | L | VL
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999
mid | -2 | -1 | 0 | 1 | 2
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5
| 0 | 0 | 0 | 0
<-- Mandatory |  | ✔
Project Plan Summary
Use this worksheet to show how much production code you plan to write and the amount of time to write it. Values are extracted from the Estimation tab.
Program Size (LOC) |  | Plan | Actual | To Date
LOC |  | 53 | 70 | 70
LOCa |  |  |  | 0
Lines added to Base |  | 0 |  | 0
Reused lines |  |  |  | 0
New lines of production code |  | 0 |  | 0
Component Count |  | Plan | Actual | To Date
Reused components |  |  |  | 0
Modified components |  |  |  | 0
New components |  |  |  | 0
Time In Phase (minutes) |  | Plan | Actual | Actual to Date | Actual to Date %
Analyze |  | 0 | 15 | 15 | 8.108%
Architect |  | 0 | 10 | 10 | 5.405%
Plan project |  | 0 | 20 | 20 | 10.81%
Plan iteration |  | 0 | 0 | 0 | 0%
Construct |  | 0 | 90 | 90 | 48.65%
Refactor |  | 0 | 30 | 30 | 16.22%
Review |  | 0 | 10 | 10 | 5.405%
Integration test |  | 0 | 0 | 0 | 0%
Repattern |  | 0 | 0 | 0 | 0%
Postmortem |  | 0 | 10 | 10 | 5.405%
Sandbox |  | 0 | 0 | 0 | 0%
TOTAL |  | 0 | 185 | 185 | 100%
Changes Identified |  |  | Actual | Actual to Date | Actual to Date %
Analyze |  |  | 0 | 0 | 0%
Architect |  |  | 0 | 0 | 0%
Plan project |  |  | 0 | 0 | 0%
Plan iteration |  |  | 0 | 0 | 0%
Construct |  |  | 0 | 0 | 0%
Refactor |  |  | 0 | 0 | 0%
Review |  |  | 0 | 0 | 0%
Integration test |  |  | 0 | 0 | 0%
Repattern |  |  | 0 | 0 | 0%
Postmortem |  |  | 0 | 0 | 0%
Sandbox |  |  | 0 | 0 | 0%
TOTAL |  |  | 0 | 0 | 0%
Changes Implemented |  |  | Actual | Actual to Date | Actual to Date %
Analyze |  |  | 0 | 0 | 0%
Architect |  |  | 0 | 0 | 0%
Plan project |  |  | 0 | 0 | 0%
Plan iteration |  |  | 0 | 0 | 0%
Construct |  |  | 0 | 0 | 0%
Refactor |  |  | 0 | 0 | 0%
Review |  |  | 0 | 0 | 0%
Integration test |  |  | 0 | 0 | 0%
Repattern |  |  | 0 | 0 | 0%
Postmortem |  |  | 0 | 0 | 0%
Sandbox |  |  | 0 | 0 | 0%
TOTAL |  |  | 0 | 0 | 0%
Note on C50: Estimate of the number of lines added to previously-written code to bring it to the point where new functionality can be added
Note on C51: Count of the number of lines of reused source code
Note on C52: Estimate the number of new lines of production code that provide new functionality to meet the specifications of this assignment.
Note on C55: Number of reusable components that will be reused.
Note on C56: Estimate of the number of previously-delivered components that will be used.
Note on C57: Estimate of the number of new components to be built.

## PlanSummary (hidden)
Project Plan Summary
Standards
Start date: | 2000-01-01 |  | Grades: | AA
End date: | 40179 |  |  | A
Phases: | Analysis |  |  | AB
| Architecture |  |  | B
| Planning |  |  | BC
| Construction |  |  | C
| Refactoring |  |  | CD
| Review |  |  | D
| Integration Test |  |  | F
Postmortem
Sandbox
Defect Types: | Documentation |  | Iteration | NA
| Build |  |  | 1
| Product syntax |  |  | 2
| Product logic |  |  | 3
| Product interface |  |  | 4
| Product checking |  |  | 5
| Test syntax |  |  | 6
| Test logic |  |  | 7
| Test interface |  |  | 8
| Test checking |  |  | 9
| Bad Smell |  |  | 10
Y/N: | Yes
No
Proxy Types: | Calculation
Data
I/O
Logic
Sizes: | VS
S
M
L
VL
|  | Plan | Actual | To Date
Program Size (LOC)
Base code LOC count |  | 0 | 0 | 0
Lines deleted from Base |  | 0 | 0 | 0
Lines modified from Base |  | 0 | 0 | 0
Lines added to Base |  | 0 | 0 | 0
Reused lines |  | #REF! | 0 | 0
New lines of production code |  | #REF! | 0 | 0
|  | Plan | Actual | To Date | To Date %
Time In Phase (minutes)
Analyze |  | 0 | 15 | 15 | 150%
Architect |  | 0 | 10 | 10 | 100%
Plan project |  | 0 | 20 | 20 | 200%
Plan iteration |  | 0 | 0 | 0 | 0%
Construct |  | 0 | 90 | 90 | 900%
Refactor |  | 0 | 30 | 30 | 300%
Review |  | 0 | 10 | 10 | 100%
Integration test |  | 0 | 0 | 0 | 0%
Repattern |  | 0 | 0 | 0 | 0%
Postmortem |  | 0 | 10 | 10 | 100%
Sandbox |  | 0 | 0 | 0 | 0%
TOTAL |  | 0 | 185 | 185 | 1850%
Changes traced to the activities below:
Analyze |  |  | 0 | 0
Architect |  |  | 0 | 0
Plan project |  |  | 0 | 0
Plan iteration |  |  | 0 | 0
Construct |  |  | 0 | 0
Refactor |  |  | 0 | 0
Review |  |  | 0 | 0
Integration test |  |  | 0 | 0
Repattern |  |  | 0 | 0
Postmortem |  |  | 0 | 0
Sandbox |  |  | 0 | 0
TOTAL |  |  | 0 | 0
Changes implemented in the activities below:
Analyze |  |  | 0 | 0
Architect |  |  | 0 | 0
Plan project |  |  | 0 | 0
Plan iteration |  |  | 0 | 0
Construct |  |  | 0 | 0
Refactor |  |  | 0 | 0
Review |  |  | 0 | 0
Integration test |  |  | 0 | 0
Repattern |  |  | 0 | 0
Postmortem |  |  | 0 | 0
Sandbox |  |  | 0 | 0
TOTAL |  |  | 0 | 0

## Change Log (hidden)
Constants |  |  |  |  | 0
Start date: | 36526 |  | Grades: | AA | 1 | 0 | 44889 | 0
End date: | 73051 |  |  | A | 0.95 | 0 | 0 | 0
Phases: | Analyze | Identifying customer needs |  | AB | 0.9 | 0 | 0 | 0
| Architect | High-level design |  | B | 0.85 | 0 | 0 | 0
| Plan project | Determine actions/effort for project duration |  | BC | 0.8 | 0 | 0 | 0
| Plan iteration | Determine actions/effort this iteration |  | C | 0.75 | 0 | 0 | 0
| Construct | Low-level design, coding, unit testing |  | CD | 0.7 | 44883 | 1 | 0
| Refactor | Restructure internal design |  | D | 0.65 | 44882 | 2 | 5
| Review | Examine test code for risk mitigation |  | F | 0.5 | 44881 | 3 | 10
| Integration test | End-to-end test of components to date |  |  |  | 44880 | 4 | 15
| Repattern | Restructure external design |  |  |  | 44879 | 5 | 20
| Postmortem | Capture post-development statistics |  |  |  | 44878 | 6 | 25
| Sandbox | Prove ideas, try concepts |  |  |  | 44877 | 7 | 30
| Previous Project |  |  |  |  | 44876 | 8 | 35
[6 empty] | 44875 | 9 | 40
[6 empty] | 44874 | 10 | 45
[6 empty] | 44873 | 11 | 50
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow | 44872 | 12 | 55
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful | 44871 | 13 | 0
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful | 44870 | 14 | 0
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral | 44869 | 15 | 0
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful | 44868 | 16 | 0
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful | 44867 | 17 | 0
| Test syntax | Syntax flaws in the test code |  | 6 |  | 44866 | 18 | 0
| Test logic | Logic flaws in the test code |  | 7 |  | 44865 | 19 | 0
| Test interface | Flaws in the interface of a component of the test code |  | 8 |  | 44864 | 20 | 0
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9 |  | 44863 | 21 | 0
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0 | 44862 | 22 | 0
Y/N: | Yes |  |  | Passed | 0 | 44861 | 23 | 0
| No |  |  | Passed with issues | 0 | 44860 | 0 | 0
Proxy Types: | - |  |  | Failed | Base | 44859 | 0 | 0
| Calculation |  |  | Not tested | New | 44858 | 0 | 0
| Data |  |  | Not applicable | Reusable | 44857 | 0 | 0
| I/O |  |  |  |  | 44856 | 0 | 0
| Logic |  |  |  |  | 44855 | 0 | 0
[6 empty] | 44854 | 0 | 0
Sizes: | VS | S | M | L | VL | VS | 0 | 0
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999 | S | 0 | 0
mid | -2 | -1 | 0 | 1 | 2 | M | 0 | 0
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5 | L | 0 | 0
| 0 | 0 | 0 | 0 |  | VL | 0 | 0
[6 empty] | 0 | 0 | 0
<-- Mandatory |  | ✔ |  |  |  | 0 | 0 | 0
Change Log
Use this worksheet to record changes to made to artifacts after the project is underway. Record repairs to defects, as well as changes that result from requirements clarifications/changes.
|  | Change Designation | Description
|  | Requirements Change | Changes to requirements
|  | Requirements Clarification | Clarifications to requirements
|  | Product syntax | Syntax flaws in the deliverable product
|  | Product logic | Logic flaws in the deliverable product
|  | Product interface | Flaws in the interface of a component of the deliverable product
|  | Product checking | Flaws with boundary/type checking within a component of the deliverable product
|  | Test syntax | Syntax flaws in the test code
|  | Test logic | Logic flaws in the test code
|  | Test interface | Flaws in the interface of a component of the test code
|  | Test checking | Flaws with boundary/type checking within a component of the test code
|  | Bad Smell | Refactoring changes (please note the bad smell in the defect description)
Change Number | Date Of Change | Change Type | Activity Where Injected | Iteration Where Injected | Activity Where Removed | Iteration Where Removed | Fix Time | Reference To A Previous Change | Description
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75

## Security (hidden)
Security Recommendation
Pick one
| Security Facet | Evil Path Acceptance Test | Recommendation for a functional specification to address security facet
Confidentiality
Integrity
Availability
Authenticity
Integrity

## Time Log
Constants | [6 empty] | 0
Start date: | 36526 |  | AA |  | Grades: | AA | 1
End date: | 73051 |  | A |  |  | A | 0.95
Phases: | Analyze | 0 | Identifying customer needs |  | AB | 0.9 | 44887 | 0
| Architect | 0 | High-level design |  | B | 0.85 | 44886 | 0
| Plan project | 0 | Determine actions/effort for project duration |  | BC | 0.8 | 44885 | 0
| Plan iteration | 0 | Determine actions/effort this iteration |  | C | 0.75 | 44884 | 0
| Construct | 0 | Low-level design, coding, unit testing |  | CD | 0.7 | 44883 | 0
| Refactor | 0 | Restructure internal design |  | D | 0.65 | 44882 | 1
| Review | 0 | Examine test code for risk mitigation |  | F | 0.5 | 44881 | 2
| Integration test | 0 | End-to-end test of components to date |  |  |  | 44880 | 3
| Repattern | 0 | Restructure external design |  |  |  | 44879 | 4
| Postmortem | 0 | Capture post-development statistics |  |  |  | 44878 | 5
| Sandbox | 0 | Prove ideas, try concepts |  |  |  | 44877 | 6
Defect Types: | Requirements Change |  | NA |  | Iteration | NA | did not follow
| Requirements Clarification |  | 1 |  |  | 1 | very painful
| Product syntax |  | 2 |  |  | 2 | painful
| Product logic |  | 3 |  |  | 3 | neutral
| Product interface |  | 4 |  |  | 4 | helpful
| Product checking |  | 5 |  |  | 5 | very helpful
| Test syntax |  | 6 |  |  | 6
| Test logic |  | 7 |  |  | 7
| Test interface |  | 8 |  |  | 8
| Test checking |  | 9 |  |  | 9
| Bad Smell |  | 10 |  |  | 10 | 0
Y/N: | Yes |  | Passed |  |  | Passed | 0
| No |  | Passed with issues |  |  | Passed with issues | 0
Proxy Types: | - |  | Failed |  |  | Failed | Base
| Calculation |  | Not tested |  |  | Not tested | New
| Data |  | Not applicable |  |  | Not applicable | Reusable
I/O
Logic
Sizes: | VS |  | L |  | M | L | VL
upper | -1.5 |  | 1.5 |  | 0.5 | 1.5 | 99999
mid | -2 |  | 1 |  | 0 | 1 | 2
lower | 0 |  | 0.5 |  | -0.5 | 0.5 | 1.5
| 0 |  | 0 |  | 0 | 0
<-- Mandatory
Time Recording Log
Use this worksheet to record the amount of time you spend on each activity. Use the "sandbox" activity to record time spent experimenting with the assignment requirements..
|  | Activity |  | Meaning
|  | Analyze |  | Identifying customer needs
|  | Architect |  | High-level design
|  | Plan project |  | Determine actions/effort for project duration
|  | Plan iteration |  | Determine actions/effort this iteration
|  | Construct |  | Low-level design, coding, unit testing
|  | Refactor |  | Restructure internal design
|  | Review |  | Examine test code for risk mitigation
|  | Integration test |  | End-to-end test of components to date
|  | Repattern |  | Restructure external design
|  | Postmortem |  | Capture post-development statistics
|  | Sandbox |  | Prove ideas, try concepts
| Start Time |  | Stop Time
Date | Hour | Min | Hour | Min | Interrupt | Delta | Activity | Iteration | Comments
2022-11-23 | 7 | 30 | 7 | 50 | 0 | 20 | Refactor | 5 | Fixed and cleaned up iteration 5 before starting iteration 6 (simple fixes and shortened some methods)
2022-11-23 | 12 | 20 | 12 | 35 | 0 | 15 | Analyze | 6
2022-11-23 | 12 | 35 | 12 | 45 | 0 | 10 | Architect | 6
2022-11-23 | 13 | 0 | 13 | 20 | 0 | 20 | Plan project | 6
2022-11-23 | 13 | 20 | 13 | 50 | 10 | 20 | Construct | 6
2022-11-23 | 16 | 20 | 16 | 50 | 0 | 30 | Construct | 6
2022-11-24 | 11 | 20 | 12 | 0 | 0 | 40 | Construct | 6
2022-11-24 | 12 | 10 | 12 | 20 | 0 | 10 | Refactor | 6
2022-11-24 | 12 | 20 | 12 | 30 | 0 | 10 | Review | 6
2022-11-24 | 12 | 30 | 12 | 40 | 0 | 10 | Postmortem | 6
2022-11-24 | 13 | 0 | 13 | 0 | 0 | 0 | Refactor | 6 | Just cleaning up one last thing I remembered

## Lessons
Lessons Learned
Problems of Importance
1
2
3
4
5
Proposal for Improvements
1
2
3
4
5
Notes and Comments
1
2
3
4
5

## Process (2) (hidden)
Constants |  |  |  | 0
Start date: | 36526 |  | Grades: | 1
End date: | 73051 |  |  | 0.95
Phases: | Analyze | Identifying customer needs |  | 0.9
| Architect | High-level design |  | 0.85
| Plan project | Determine actions/effort for project duration |  | 0.8
| Plan iteration | Determine actions/effort this iteration |  | 0.75
| Construct | Low-level design, coding, unit testing |  | 0.7
| Refactor | Restructure internal design |  | 0.65
| Review | Examine test code for risk mitigation |  | 0.5
| Integration test | End-to-end test of components to date
| Repattern | Restructure external design
| Postmortem | Capture post-development statistics
| Sandbox | Prove ideas, try concepts
Defect Types: | Requirements Change | Changes to requirements | Iteration | did not follow
| Requirements Clarification | Clarifications to requirements |  | very painful
| Product syntax | Syntax flaws in the deliverable product |  | painful
| Product logic | Logic flaws in the deliverable product |  | neutral
| Product interface | Flaws in the interface of a component of the deliverable product |  | helpful
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | very helpful
| Test syntax | Syntax flaws in the test code
| Test logic | Logic flaws in the test code
| Test interface | Flaws in the interface of a component of the test code
| Test checking | Flaws with boundary/type checking within a component of the test code
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 0
Y/N: | Yes |  |  | 0
| No |  |  | 0
Proxy Types: | - |  |  | Base
| Calculation |  |  | New
| Data |  |  | Reusable
I/O
Logic
Sizes: | VS | S | M | VL
upper | -1.5 | -0.5 | 0.5 | 99999
mid | -2 | -1 | 0 | 2
lower | 0 | -1.5 | -0.5 | 1.5
| 0 | 0 | 0
<-- Mandatory |  | ✔
Process Script
Minimal Guiding Indicators |  |  |  | Minimal Sufficient Activities
| Goal | Indicator |  |  | Engineering Activities
| Cost: | None |  |  | Envision
| Schedule: | On time |  |  | Analyze
| Performance: |  |  |  | Synthesize
| Product: |  |  |  | Architecture
| NFR: | None |  |  | Articulate
| FR: | Equivalence Class Partitioning |  |  | Construct
| Process: | Completed spreadsheet |  |  | Interpret
Integration Test
Operational Activities
Plan
Plan project
Monitor/Control
Post Mortem
Release
Minimal Viable Process |  |  |  | Minimal Effective Practices
|  |  |  | MSA | MEP | Spreadsheet tab on which to document MEP
|  |  |  | Pre-project | • Switch to an iteration-specific local branch
|  |  |  | Analysis | • Write as many acceptance tests as you feel are necessary to understand the assignment | Acceptance
|  |  |  | Architect | • Create CRC cards for each component you plan to build/modify | Architecture - Pre
|  |  |  | Plan Project | • Estimate projected LOC | Estimation
[5 empty] | • Estimate projected effort | Estimation
[5 empty] | • Estimate schedule | Schedule
[5 empty] | • Construct review check list | Review
|  |  |  | Construction | • Repeat
• • Select/write a test case
[5 empty] | • • Run the test as a red light test | Acceptance (if test is an acceptance test)
• • While the test is not red
• • • Diagnose why the test was not red
• • • If the problem was due to incorrect test code
• • • • Fix the defect
• • • • Run the test as a red light test
• • • Else
• • • • Continue to the next red light test
• • Build enough production code to make the test pass
• • Run the test as a green light test
• • While the test is not green
• • • Fix the defect
• • • Run the test as a green light test
• • Clean up the code as appropriate and run as blue light
• Until test coverage is sufficient and all tests pass
|  |  |  | Review | • Perform rubber duck review of test code | Review
|  |  |  | Refactor | • Refactor production code to remove odious smells; run as blue light
|  |  |  | Post Mortem | • Record acceptance test results | Acceptance
[5 empty] | • Count production LOC | Estimation
[5 empty] | • Record actual schedule | Schedule
[5 empty] | • Record your CRC cards as of the time of submission | Architecture - Post
|  |  |  | Release | • Record lessons learned (optional) | Lessons
• Commit all code to git
• Push branch to GitHub
• Merge iteration branch with master branch
• Push master branch to GitHub.com
Minimal Guiding Indicators |  |  |  | Monitor | • Upload spreadsheet to Canvas
Cost: |  | - |  |  | • Record time spent in each activity. | Time Log
Schedule: |  | Submitted on time
Performance:
Product:
| NFR: | Meets delivery requirements.
| FR: | Boundary Value Analysis
| Process: | Evident on spreadsheet
Operational Engineering
Plan Project
Post Mortem
Release
Monitor
Construct
Not all components are constructed
Analyze
Review
Failed review
Refactor
Architect

## Source (hidden)
Source Code
Paste production source code here. (1) copy your code to the clipboard, (2) click on the "PASTE ME" cell (not the entire row), (3) paste. Do not paste test code.
PASTE ME

## Constants (hidden)
Constants | [5 empty] | 0
Start date: | 2000-01-01 |  |  | Grades: | AA | 100% | 2022-11-24 |  | 2022-11-24
End date: | 2100-01-01 |  |  |  | A | 95% | 2022-11-23
Phases: | Analyze |  | Identifying customer needs |  | AB | 90% | 2022-11-22
| Architect |  | High-level design |  | B | 85% | 2022-11-21
| Plan project |  | Determine actions/effort for project duration |  | BC | 80% | 2022-11-20
| Plan iteration |  | Determine actions/effort this iteration |  | C | 75% | 2022-11-19
| Construct |  | Low-level design, coding, unit testing |  | CD | 70% | 2022-11-18 | 0 | 0 | AM
| Refactor |  | Restructure internal design |  | D | 65% | 2022-11-17 | 1 | 5 | PM
| Review |  | Examine test code for risk mitigation |  | F | 50% | 2022-11-16 | 2 | 10
| Integration test |  | End-to-end test of components to date |  |  |  | 2022-11-15 | 3 | 15
| Repattern |  | Restructure external design |  |  |  | 2022-11-14 | 4 | 20
| Postmortem |  | Capture post-development statistics |  |  |  | 2022-11-13 | 5 | 25
| Sandbox |  | Prove ideas, try concepts |  |  |  | 2022-11-12 | 6 | 30
[7 empty] | 2022-11-11 | 7 | 35
[7 empty] | 2022-11-10 | 8 | 40
[7 empty] | 2022-11-09 | 9 | 45
[7 empty] | 2022-11-08 | 10 | 50
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow |  | 2022-11-07 | 11 | 55
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful |  | 2022-11-06 | 12
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful |  | 2022-11-05 | 13
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral |  | 2022-11-04 | 14
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful |  | 2022-11-03 | 15
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful |  | 2022-11-02 | 16
| Test syntax | Syntax flaws in the test code |  | 6 |  |  | 2022-11-01 | 17
| Test logic | Logic flaws in the test code |  | 7 |  |  | 2022-10-31 | 18
| Test interface | Flaws in the interface of a component of the test code |  | 8 |  |  | 2022-10-30 | 19
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9 |  |  | 2022-10-29 | 20
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 |  |  | 2022-10-28 | 21
Y/N: | Yes |  |  | Passed |  |  | 2022-10-27 | 22
| No |  |  | Passed with issues |  |  | 2022-10-26 | 23
Proxy Types: | - |  |  | Failed | Base |  | 2022-10-25
| Calculation |  |  | Not tested | New |  | 2022-10-24
| Data |  |  | Not applicable | Reusable |  | 2022-10-23
| I/O | [5 empty] | 2022-10-22
| Logic | [5 empty] | 2022-10-21
2022-10-20
Sizes: | VS | S | M | L | VL | VS
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999 | S
mid | -2 | -1 | 0 | 1 | 2 | M
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5 | L
VL
<-- Mandatory |  | ✔